## Start Here
THE OPERATING CADENCE
A three-touch weekly system that keeps the record current. cnnctd.work
WHAT THIS ACTUALLY IS
Monday you find out what is genuinely stuck, rather than what people would prefer you believed. Wednesday
you clear it. Friday you write down what really happened. The meetings are not the point. The point is that
the record gets updated inside the touch, so the board cannot quietly drift away from reality while
everyone in the room stays perfectly polite about it.
WHICH SHEETS YOU TYPE ON
DISCOVERY — twenty minutes, once, before you start. It sets the baseline everything else is measured against.
BOARD — the sheet you live in. One row per item of work in flight.
WEEKLY LOG — one row per touch, thirty seconds at the end of it.
DECISION LOG — anything decided during a touch, so it stays decided.
TREND — five numbers off Health, once a week, pasted as values.
SNAPSHOT — three boxes, after four weeks, then send the file back.
WHICH SHEETS TYPE FOR YOU
HEALTH — reads the Board and tells you whether the cadence is working. Do not type here.
THRESHOLDS — the numbers Health judges against. Change these, but change them for a reason.
COLOUR CONVENTION
BLUE text on pale blue = you type here.
GREY text on pale grey = calculated. Leave it alone, including when you dislike the answer.
GREEN text on pale green = a setting you are allowed to tune.
THE ONE RULE THAT MATTERS
Update the Board during the touch, not after it. A board updated afterwards is a meeting with homework,
and homework does not get done. If you defer the recording, you do not have a cadence. You have a standing
appointment where people take turns sounding busy.
THE EXAMPLE ROWS ARE NOT YOURS
Rows 7 to 10 on the Board are made up. They exist so Health has something to chew on and you can
see what a flag looks like before your own numbers start doing it to you. Delete them before you use this
for real, and do not be surprised when your first week looks worse than the examples. Everyone's does.
THIS IS FREE. THE ARTIFACT WAS NEVER THE HARD PART.
Running it for eight weeks when it is inconvenient is the hard part. So is being the person who reads the
carryover number out loud when it says 60%. If you want somebody in the room while that becomes normal,
the Snapshot sheet at the end tells you how. If you do not, keep the file anyway. It works the same.

## Discovery
DISCOVERY
Twenty minutes, once. Answer honestly or do not bother — a flattering version of this is worthless to you.
QUESTION | YOUR ANSWER | WHY WE ASK
THE SHAPE OF IT
What is true in 90 days that is not true today? |  | If this needs more than one sentence, that is itself the finding. Vague outcomes are why the work never visibly finishes.
What are you explicitly not doing? |  | Non-goals are the only part of scope anyone remembers once things get tight. A project without them absorbs everything nearby.
What breaks if nothing changes? |  | If nothing breaks, this is a preference rather than a project. Both are legitimate. They are priced and sequenced very differently.
WHO DECIDES
Who decides what is in scope? |  | One name. 'The leadership team' means nobody, and it is the most expensive answer on this sheet.
Who decides when two priorities collide? |  | This person exists whether or not you name them. Naming them saves about a day a week.
Who decides money? |  | Often a different person from the two above, which is fine, as long as everyone knows it.
Who gets to say a thing is finished? |  | If nobody owns 'done', work does not finish. It just gradually stops being discussed.
WHO DOES THE WORK
Names, and hours per week each one actually has for this |  | Actually has. Not the hours their job title implies, and not the hours they would have in a good week.
Who is the single point of failure right now? |  | Everyone already knows. Writing it down is what makes it a risk you are managing rather than one you are hoping about.
THE CONSTRAINT
What is the binding constraint? |  | Only one can be binding at a time. Picking two means you have not found it yet, and you will optimise the wrong thing at speed.
What have you already tried? |  | Saves you paying us to suggest it again with a different name on it.
Why did it not hold? |  | Almost always the answer is that it required someone to remember something. Systems beat memory, every time.
THE RECORD TODAY
Where does work live right now? List every place. |  | Count them honestly. Three is common. Three is also the problem — nobody can hold three sources of truth in their head, so they stop trying.
How does anyone find out that something finished? |  | If the honest answer is 'someone mentions it', your record lag is not a number you have. It is a rumour.
Last thing that slipped — and when you found out |  | The gap between those two dates is the entire reason this workbook exists. Write both.
CADENCE BASELINE
Recurring meeting hours per week, per person |  | All standing meetings, not just this project's. Be generous — the point is the real number.
How many people sit in them |  | Headcount actually in the room, including the ones who never speak.
How many of those produce a written outcome? |  | A meeting with no written outcome is a conversation. Conversations are useful. They are not a record, and they cannot be handed to anyone.
What does good look like, in one sentence? |  | If you and the person next to you write different sentences here, that gap is the project.
WHAT YOUR MEETINGS CURRENTLY COST
Person-hours per week, in recurring meetings |  | Calculated. Hours per person times people.
Person-hours per year, at 48 working weeks |  | This is not an argument for fewer meetings. It is the budget you are already spending on coordination, whether or not it is producing a record.

## Board
BOARD
One row per item in flight. You fill the blue columns; the last five calculate themselves.
ITEM | OWNER | STATUS | FIRST SURFACED | LAST UPDATED | BLOCKED SINCE | UNBLOCK BY | DONE (IN REALITY) | RECORDED ON BOARD | WEEKS CARRIED | BLOCK AGE | RECORD LAG | DAYS SILENT | WHAT IS WRONG WITH THIS ROW
Migrate billing exports to the new schema | Dana | Blocked | 2026-08-12 | 2026-08-29 | 2026-08-27 |  |  |  | 3 | 11 |  | 9 | No unblock date. Nobody owns this one.
Q3 renewal outreach — top 12 accounts | Marcus | Active | 2026-08-26 | 2026-09-06 |  |  |  |  | 1 |  |  | 1
Rewrite the onboarding checklist | Dana | Done | 2026-08-19 | 2026-09-05 |  |  | 2026-08-30 | 2026-09-05 | 1 |  | 6 |  | Recorded 6 days late. The board is lagging.
Vendor security review | Priya | Blocked | 2026-08-05 | 2026-08-18 | 2026-08-22 | 2026-09-10 |  |  | 4 | 16 |  | 20 | Blocked 16 days. That is a decision, not a block.
Formulas:
WEEKS CARRIED = IF([FIRST SURFACED]="","",IF([DONE (IN REALITY)]<>"",ROUNDDOWN(([DONE (IN REALITY)]-[FIRST SURFACED])/7,0),ROUNDDOWN((TODAY()-[FIRST SURFACED])/7,0)))
BLOCK AGE = IF(OR([STATUS]<>"Blocked",[BLOCKED SINCE]=""),"",TODAY()-[BLOCKED SINCE])
DAYS SILENT = IF(OR([LAST UPDATED]="",[STATUS]="Done"),"",TODAY()-[LAST UPDATED])

## Health
HEALTH
Reads the Board and tells you the truth about it. Do not type on this sheet.
SIGNAL | VALUE | VERDICT | WHAT IT MEANS WHEN IT IS OFF
Items in flight (not done) | 3 |  | Your real work in progress, not the version in the deck. If it climbs every week you are starting faster than you are finishing, and that is a choice somebody is making without saying so.
Blocked items | 2 |  | Blocked is honest and completely fine. Blocked and unsaid is what actually costs you the quarter.
Blocked with no unblock date | 1 | CHECK | Anything above zero is a block nobody has agreed to own. Fastest thing on this sheet to fix, and the most revealing that it needed fixing.
Oldest block (days) | 16 | CHECK | Past the threshold, stop calling it a block. Somebody will not decide. Escalate it or kill the item. A third option is not available, however long the meeting runs.
Items carried past the threshold | 2 | CHECK | Long-carried items are scoped wrong or unowned. Split them, decide them, or delete them. Listing them again is not a plan, it is a habit.
Carryover rate | 100% | CHECK | Above the threshold your weekly commitment is aspirational. Halve what you commit to for three weeks and let people feel what finishing is like. They may not remember.
Average record lag (days) | 6 | CHECK | The gap between finishing and the board knowing. This is the number that decides whether you have an operating view or a decoration.
Items silent past the threshold | 1 | CHECK | Nobody has touched these. They are not paused, they are abandoned. Abandoning things on purpose is allowed and often correct. Abandoning them by accident is what costs you.
Items flagged, any reason | 3 | CHECK | Your Wednesday agenda in one number. If this is zero every single week, either you are genuinely excellent or nobody is telling you anything.
How to read this sheet
Every CHECK is a conversation, not a failing grade. Run your eye down the verdict column on Wednesday and work the black ones. If everything says OK for six weeks running, you have earned the right to loosen.
WHEN TO LOOSEN THE CADENCE
3 touches to 2 | Carryover under 25% for four straight weeks AND no block has gone undated.
2 touches to 1 | Average record lag at or under one day for six weeks AND nothing has gone silent.
Straight back up | The moment carryover clears 40% two weeks running. Loosening is reversible, and treating it that way is what stops it becoming a status symbol.

## Trend
TREND
Five numbers off Health, once a week. Ten seconds. It is the only way you ever see the shape of it.
WEEK ENDING | IN FLIGHT | CARRYOVER | AVG RECORD LAG | FLAGGED | VERSUS LAST WEEK
Paste values, not formulas
Every Friday, copy the five numbers off Health and paste them here as values. One week of data tells you nothing. Four weeks tells you whether the rhythm is holding. Nobody has ever regretted having the trend, and plenty of people have argued for an hour about a number they could have written down.

## Thresholds
THRESHOLDS
The numbers Health judges against. Yours to change once you know your own baseline.
SETTING | VALUE | WHY THIS NUMBER
Carried weeks before an item is flagged | 3 | Under three weeks is ordinary drift. At three the item is scoped wrong or nobody actually owns it. Listing it a fourth time is a decision to keep pretending.
Block age in days before it is flagged | 7 | A block that survives a week is not a block. It is a decision nobody wants to make, wearing a block for cover.
Record lag in days before it is flagged | 2 | Days between something finishing in reality and the board finding out. Above two you do not have an operating view. You have a newsletter.
Days silent before an item is flagged | 14 | Untouched for a fortnight. Nobody paused these. They died, and they are still taking up room in everyone's head.
Carryover rate that means the week is fiction | 40% | Share of live work already older than a week. Above 40% your weekly plan is fiction, and everyone in the room has privately worked that out already.
Change these, but change them for a reason
Defaults are a starting position, not a standard. Run four weeks, see what your own numbers do, then move one number at a time. Loosening every threshold until nothing flags is not tuning. It is turning the smoke alarm off because it keeps going off.

## Weekly Log
WEEKLY LOG
One row per touch. Thirty seconds at the end of it. This is why next Monday is fast.
DATE | TOUCH | WHAT SURFACED | WHAT GOT UNBLOCKED | WHAT SHIPPED OR CLOSED | CARRIED OVER — AND WHY
2026-09-03 | Monday — expose | Vendor security review still stuck, and nobody had a date for it |  |  | Billing schema — waiting on Dana's access request

## Decision Log
DECISION LOG
The sheet that stops the same block resurfacing in three weeks wearing a new name.
DATE | DECISION | MADE BY | BECAUSE | REVISIT IF
2026-09-03 | Ship the billing migration without the legacy export | Marcus | Two customers use it and both have agreed to the new format | A third customer asks for the legacy export before Q4

## Snapshot
SNAPSHOT
Four weeks in, send this file back. It is the whole of our first conversation.
Run the cadence for four weeks, fill in the three boxes below, and email this workbook to connect@cnnctd.work. The numbers fill themselves in from your Board, including the ones you would rather not send. Those are the useful ones.
PULLED FROM YOUR DISCOVERY SHEET
What you said good looks like | — not filled in —
The binding constraint | — not filled in —
Person-hours a week in meetings | —
PULLED FROM YOUR BOARD
Items in flight | 3
Carryover rate | 100%
Oldest block (days) | 16
Blocked with no date | 1
Average record lag (days) | 6
Items currently flagged | 3
These calculate themselves. Do not type over them, and do not tidy them up.
WHAT WE CANNOT COMPUTE
Company or team, and who runs the cadence
What is still not working
What you want to be true in 90 days
WHAT HAPPENS NEXT
We read the file before we talk. That means the first conversation starts from your actual numbers instead of an hour spent rebuilding them out loud while everyone nods.
If the numbers say your cadence is holding, we will tell you that and go away. It happens more often than you would expect, and it is a perfectly good outcome for everybody involved.
We do not share this file, we do not sell it on, and we do not add you to anything. connect@cnnctd.work — cnnctd.work